## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Self | 24/10/2025 | Speech recognition accuracy drops in noisy environment | Sprint 1 | Self | Functional | Added noise filtering and re-trained model | 26-10-2025 | Closed | Issue resolved
2 | Self | 2025-01-11 | Delay in text-to-speech audio response | Sprint 2 | Self | Performance | Optimized response generation logic | 2025-03-11 | Closed | Improved response time
3 | Self | 2025-10-11 | JSON file overwriting previous conversation data | Sprint 3 | Self | Data Handling | Fixed append logic for JSON storage | 2025-12-11 | Closed | Data stored correctly
4 | Self | 20/11/2025 | Microphone permission error on UI launch | Sprint 4 | Self | UI | Added permission handling and fallback | 22-11-2025 | Closed | UI works as expected
5 | Self | 2025-02-12 | Incorrect intent detected for similar voice queries | Sprint 5 | Self | Functional | Improved intent classification rules | 2025-05-12 | Closed | Accuracy improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others